## Report
Project Name | Enterprise Project Type | Project Owner | % Complete | Start | Finish | Cost | Baseline Cost | Cost Variance | Work | Baseline Work | Work Variance
Acquisition Target Analysis | Enterprise Project | Ali Al | 0 | 2017-03-01 08:00 | 2017-06-02 17:00 | 97200 | 97200 | 0 | 720 | 720 | 0
Apparel ERP Upgrade | Enterprise Project | Ali Al | 42 | 2017-05-08 08:00 | 2017-10-06 17:00 | 99940 | 99940 | 0 | 1532 | 1532 | 0
Asset Tracking System | Enterprise Project | Ali Al | 20 | 2017-04-19 08:00 | 2017-12-01 15:00 | 148480 | 140880 | 7600 | 2562 | 2402 | 160
Asset-Change Ownership | Enterprise Project | Ali Al | 1 | 2017-06-12 08:00 | 2017-11-09 17:00 | 101060 | 101060 | 0 | 1548 | 1548 | 0
Audit Tracking Solution | Enterprise Project | Ali Al | 5 | 2017-04-26 08:00 | 2017-09-25 17:00 | 100660 | 99940 | 720 | 1548 | 1532 | 16
Auditing Services Training | Enterprise Project | Ali Al | 18 | 2017-02-01 08:00 | 2017-10-16 12:00 | 50100 | 60580 | -10480 | 1678 | 624 | 1054
AutoComplete CustomField | Enterprise Project | Sunil Guntupalli | 0 | 2017-08-26 08:00 | 2017-08-26 08:00 | 0 |  | 0 | 0 |  | 0
AutoComplete CustomField1 | Enterprise Project | Parthiv Bhuta | 0 | 2017-08-28 08:00 | 2017-08-28 08:00 | 0 |  | 0 | 0 |  | 0
AutoComplete CustomField2 | Enterprise Project | Karam Mohammed | 0 | 2017-08-28 08:00 | 2017-08-28 08:00 | 0 |  | 0 | 0 |  | 0
Catalog Publishing | Enterprise Project | Ali Al | 0 | 2017-08-03 08:00 | 2017-12-29 17:00 | 99940 | 99940 | 0 | 1532 | 1532 | 0
Company Portal Database Migration | Enterprise Project | Ali Al | 0 | 2017-07-06 08:00 | 2018-01-26 15:00 | 139760 | 139760 | 0 | 2386 | 2386 | 0
Compliance Database System Implementation | Enterprise Project | Ali Al | 0 | 2017-10-12 08:00 | 2018-02-20 17:00 | 62180 | 62180 | 0 | 940 | 940 | 0
Content Filtering Firewall Design and Implementation | Enterprise Project | Ali Al | 100 | 2017-01-20 08:00 | 2017-08-22 15:00 | 142880 | 139400 | 3480 | 2434 | 2378 | 56
Corporate Web Site Server Software Upgrade | Enterprise Project | Ali Al | 0 | 2017-06-14 08:00 | 2017-11-09 17:00 | 99940 | 99940 | 0 | 1532 | 1532 | 0
Data Exchange and Integration | Enterprise Project | Ali Al | 44 | 2017-02-25 08:00 | 2017-09-08 17:00 | 111820 | 99940 | 11880 | 1796 | 1532 | 264
Data Parsing Tool Implementation | Enterprise Project | Ali Al | 0 | 2017-09-04 08:00 | 2021-01-27 11:54 | 757720.11 | 757720.11 | 0 | 10648.6559 | 10648.6559 | 0
Karam Test | Enterprise Project | Karam Mohammed | 0 | 2017-09-26 08:00 | 2017-09-26 08:00 | 0 |  | 0 | 0 |  | 0
Plan for upgrade to Project Server 2013 update | Enterprise Project | SQL Admin | 3 | 2017-12-30 08:00 | 2017-08-29 10:24 | 0 |  | 0 | 30 |  | 30
Software Design Architecture Upgrade | Enterprise Project | Ali Al | 27 | 2017-03-14 08:00 | 2017-10-03 17:00 | 114020 | 100700 | 13320 | 1848 | 1540 | 308
Software Installation Automation | Enterprise Project | Ali Al | 0 | 2017-05-23 08:00 | 2017-12-11 15:00 | 129040 | 129040 | 0 | 2370 | 2370 | 0
Strategic Merger Evaluation | Enterprise Project | Ali Al | 0 | 2017-10-14 08:00 | 2018-01-17 17:00 | 0 |  | 0 | 720 |  | 720
Web Site Infrastructure Administration | Enterprise Project | Ali Al | 0 | 2017-09-15 08:00 | 2018-02-16 17:00 | 22140 | 103060 | -80920 | 1572 | 1572 | 0
Grand Total | [5 empty] | 2276880.11 | 2331280.11 | -54400 | 37396.6559 | 34788.6559 | 2608
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.